2015 Hospitality Studies Subject Improvement Framework (FET)

| GRADE | SUBJECT | IDENTIFIED WEAKNESSES | REMEDIAL MEASURE RESPONSIBILITY |  |  |  |  | Time Frames |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | DBE | PED | District | Teachers | Resources |  |
| 10 | Hospitality Studies | Learners lack basic foundational knowledge and subject terminology Learners lack deep understanding of concepts and are unable to explain basic terminology. | Develop terminology guide on these topics: Sectors and careers, Kitchen and restaurant operations and Food and beverage service | Mediate the guides to district officials. Distribute study guides to schools. Monitor and support training in the districts. | Identify and address gaps in teacher content knowledge Mediate the study guides for teachers Support, guide and monitor performance in the challenging content. Conduct demonstration lessons in the challenging content areas. | Teachers must teach basic concepts and terminology before teaching the topic and constantly test understanding. Basic concepts and terminology must continuously be reinforced and revised to improve learner’s basic understanding of each topic. Teachers must use the appropriate subject terminology during teaching to expose learners to the meaning of the concepts. | - Terminology guide - Textbooks | Jan – Dec 2015 |
|  |  | Poor understanding of action verbs: Learners could not respond to the action verbs used in the question. | Develop guide outlining expected responses to higher order questions | - Distribute and mediate guide to Subject Advisors - Monitor teacher training and implementation at school level | - Distribute and mediate guide to Teachers. - Apply guidelines in context | - Teach learners how to respond to higher order questions. - Set sample questions for informal and formal tests | - Textbooks - Guide book | Jan – Dec 2015 |
|  |  | Lack of basic comprehension skills: Inability to interpret texts; Inability to answer questions using own words; Inability to infer meaning, i.e. implied/literal/figurative | Develop and distribute basic guide on visual literacy and how to use and respond to visual stimuli | Provincial officials to print and mediate the document | District officials to distribute and mediate the document | Practise regularly in class to reinforce skills. Expose learners to various forms of visual stimuli and how to respond appropriately. | Past question papers. LAC application guide | Jan – Dec 2015 |
|  | Grade 11 | Learners lack basic foundational knowledge Learners struggled to answer basic knowledge questions, they are unfamiliar with terminology and concepts | Develop terminology guide on the following topics: Sectors and careers, Kitchen and restaurant operations and Food and beverage service | Mediate the guides to district officials. Distribute study guides to schools. Monitor and support training in the districts. | Identify and address gaps in teacher content knowledge Mediate the study guides for teachers Support, guide and monitor performance in the challenging content. Conduct demonstration lessons in the challenging content areas. | Teachers must teach basic concepts and terminology before teaching the topic and constantly test understanding. Basic concepts and terminology must continuously be reinforced and revised to improve learner’s basic understanding of each topic. Teachers must use the appropriate subject terminology during teaching to expose learners to the meaning of the concepts. | Mediate the guides to district officials. Distribute study guides to schools. Monitor and support training in the districts. | Jan – Dec 2015 |
|  |  | Poor understanding of action verbs: Learners could not respond to the action verbs used in the question. | Compile document to explain common action verbs and the expected responses, | Provincial officials to print and mediate the document | The district officials distribute, mediate and monitor the utilisation of the document. | Ensure all formal and informal assessment comply quality and validity criteria Learners to be taught the meaning of action verbs Use previous question papers as a teaching tool and informal assessment tool to expose learners to the different types of questions being asked and how to respond appropriately | Textbooks Previous question papers | Jan – Dec 2015 |
|  |  | Poor response to higher order questions: Lack of sound reasoning ability and are unable to express themselves clearly. | Develop guide outlining expected responses to higher order questions | - Distribute and mediate guide to Subject Advisors - Monitor teacher training and implementation at school level | - Distribute and mediate guide to Teachers. - Apply guidelines in context | - Teach learners how to respond to higher order questions. - Set sample questions for informal and formal subjects | Textbooks Guidelines | Jan – Dec 2015 |
|  | Grade 12 | The basic knowledge from grade 10 and 11 and 12 of learners is limited. Learners lack deep understanding of concepts and are unable to explain basic terminology. Learners struggled to answer basic knowledge questions, they are unfamiliar with terminology and concepts | - Develop terminology guide on these topics: Sectors and careers, Kitchen and restaurant operations and Food and beverage service. - Compile and distribute a basic and concept terminology list per topic | - Mediate the study guides to district officials. - Distribute study guides to schools. - Monitor and support training in the districts. | - Identify and address gaps in teacher content knowledge - Mediate the study guides for teachers - Support, guide and monitor performance in the challenging content. - Conduct demonstration lessons in the challenging content areas. | - Teachers must teach basic concepts and terminology before teaching the topic and constantly test understanding. Basic concepts and terminology must continuously be reinforced and revised to improve learner’s basic understanding of each topic. Teachers must use the appropriate subject terminology during teaching to expose learners to the meaning of the concepts. | - Textbooks - Terminology lists | Jan – Dec 2015 |
|  |  | Poor understanding of action verbs: Learners could not respond to the action verbs used in the question. | Compile document to explain common action verbs and the expected responses, | Provincial officials to print and mediate the document | The district officials distribute, mediate and monitor the utilisation of the document. | - Learners must be taught the meanings of action verbs - Use previous question papers as a teaching tool and informal assessment tool to expose learners to the different types of questions being asked and how to respond appropriately | Textbooks Past question papers. | Jan – Dec 2015 |
|  |  | Poor response to higher order questions: Lack of sound reasoning ability and are unable to express themselves clearly. Learners struggled evaluate and if they did, many could not explain the reason for their opinion or make a deduction. They could not substantiate their choice, indicating limited or no understanding of a topic. | Use previous question papers as a teaching tool and informal assessment. | Offer training to district officials on the use of past question papers | Ensure all schools have copies of past question papers Offer training to teachers on the use of past question papers | Teach learners how to respond to evaluation questions. Set questions requiring various cognitive abilities as part of teaching and informal assessment. Teach learners how to substantiate answers, this will ensure that learners are exposed to the way content can be tested and the type of questions that can be asked. Practice the skill of responding to higher order questions in class. | - Textbooks - Terminology lists - Past question papers | Jan – Dec 2015 |
|  |  | Learners misread / misinterpret questions: Learners struggled to identify the gist of questions leading to incorrect responses. | Develop and distribute examples of how to identify the crux of a question from the 2014 NSC Hospitality Studies examination paper | Provincial officials to print and mediate the document | District officials to distribute and mediate the document | Teach learners the skills of analysing a question to determine the focus of the question. | 2014 Examination guide | Jan – Dec 2015 |
|  |  | Lack of basic comprehension skills: Inability to interpret texts; Inability to answer questions using own words; Inability to infer meaning, i.e. implied/literal/figurative | Develop and distribute basic guide on visual literacy and how to use and respond to visual stimuli | Provincial officials to print and mediate the document | District officials to distribute and mediate the document | Practise regularly in class to reinforce skills. Expose learners to various forms of visual stimuli and how to respond appropriately. | Past question papers. LAC application guide | Jan – Dec 2015 |
|  |  | Menu and Recipe Calculations: Learners struggle to perform calculations relating to costing. | Distribute lessons on calculations to provinces | Print and distribute lessons to districts Offer methodology training to advisors on how to teach the topic | Offer content training to teachers Distribute self study guide to schools Offer methodology training to teachers on how to teach the topic | Develop short (10 minute) informal monthly tests on costing to keep skills current. Learners lack basic theoretical knowledge about calculations relating to menu and meal costing; Lack of arithmetical skills. Learners are not given regular calculation exercises to practice. | Past question papers Textbook | Jan – Dec 2015 |
|  |  | Paragraph responses: Showed a lack of in-depth knowledge. Candidates were not able to provide enough detail to earn full marks. Many learners struggled to express themselves in paragraph format. | Set exemplar paragraph questions on various topics. Mediate LAC processes. Provide examples of how to infuse LAC into tourism lessons | Offer training on paragraph writing using exemplars. Provincial officials train district officials on language across curriculum. | Provincial officials train teachers on the application of language across curriculum. | Teachers must teach paragraph writing skills to learners. Expose learners to the various types of paragraphs. Infuse LAC into all topics and focus on developing and strengthening the 4 language pillars | Textbook LAC booklet | Jan – Dec 2015 |